## Overview
Notion Finance Development Plan
Updated 2026-07-04. Backend plan is aligned to the current read-only Accounts, Income Categories, and Expense Categories design while frontend implementation remains in progress and Notion remains the source of truth.
Plan Sheet | Total | Not Started | In Progress | Implemented | Blocked | Needs Decision | Deferred
frontend-dev-plan | 17 | 0 | 14 | 3 | 0 | 0 | 0
backend-dev-plan | 21 | 21 | 0 | 0 | 0 | 0 | 0
integration-dev-plan | 19 | 19 | 0 | 0 | 0 | 0 | 0
testing-dev-plan | 17 | 17 | 0 | 0 | 0 | 0 | 0
Status Legend
Not Started | Planned but not yet started. |  | What is right | Auth, account delete, storage, sync order, schema verification, testing direction, deployment targets, and app sections now have clear decisions.
In Progress | Actively being worked. |  | What changed | Monthly Monitoring is now read-only in scope; specialized monthly workflows are explicit; forms hide non-context fields.
Implemented | Complete and verified for the phase. |  | Storage call | PostgreSQL is primary. Redis is optional for cache, rate limits, short-lived sessions, or queue coordination.
Blocked | Cannot proceed without access, dependency, or external action. |  | Testing setup | Destructive tests will use a duplicated Notion space provided by the project owner.
Needs Decision | Requires product, security, architecture, or delivery choice. |  | Recommended next move | Document duplicated Notion access details, confirm compact/detail fields, and confirm live relation/category mappings during backend implementation discovery.
Deferred | Intentionally postponed out of the current slice. |  | Practical warning | Do not let Redis become the source of truth for sync logs or conflicts. That job belongs to PostgreSQL.
Resolved Decisions
Decision | Plain Language | Current State | Owner Role
Login / Access | Use email sign-in and Google sign-in so other people can use the app. | Resolved | Product, Security
Reference Data Maintenance | Accounts, income categories, and expense categories are maintained in Notion only; the app exposes reads only. | Resolved | Product, Backend
Testing Space | Use a duplicated Notion space for destructive tests. | Resolved; access pending | Owner, SQA
Implementation Trigger | Create real app code only when the user says implement. | Resolved | All
Metadata Storage | Use PostgreSQL as primary durable storage; Redis is optional support. | Resolved | Backend, DevOps
Sync Order | Pull from Notion first, write updates, then pull fresh Notion data again. | Resolved | Frontend, Backend
Schema Check | Provide a button to verify schema after the integration key is configured. | Resolved | Frontend, Backend
Deployment | Use Vercel for frontend and Render for backend, with local dev/prod-style env switching. | Resolved | DevOps
App Sections | Use Dashboard, Accounts, Income, Expense, Monthly Monitoring, Transfer, Credit Card Payment, Alkansya, and Receivables. | Resolved | Product, Frontend
Monthly Monitoring | Show Monthly Monitoring as read-only monitoring; do not edit it through normal app flows. | Resolved | Product, Backend
Income Form | Normal Income forms hide transaction-only fields and auxiliary categories. | Resolved | Product, Frontend
Expense Form | Expense fields adapt to account/category/view; credit-card and Pasabuy fields show only when relevant. | Resolved | Product, Frontend

## frontend-dev-plan
frontend-dev-plan
Use Status, Blocked / Decision Needed, Verification / Evidence, and Acceptance Criteria together. A row is not done just because code exists. It is done when the acceptance criteria are verified.
ID | Priority | Phase | Epic | Work Item | Owner Role | Dependencies | Acceptance Criteria | Status | Blocked / Decision Needed | Verification / Evidence | Source Docs | Notes | Last Updated
FE-001 | P0 | Planning | UX Architecture | Confirm MVP information architecture and navigation | Frontend UI/UX Developer | Product scope and user flow docs | Dashboard, Accounts, Income, Expense, Monthly Monitoring, Transfer, Credit Card Payment, Alkansya, Receivables, sync center, settings, and error states are mapped before scaffolding | Implemented |  | Mapped app-first IA into Next.js routes for Dashboard, Accounts, Income, Expense, Monthly Monitoring, Transfer, Credit Card Payment, Alkansya, Receivables, Sync Center, and Settings; build passed. | wiki/product-specification/product-specification.md; wiki/diagrams/user-flow.md | Prototype shell patterns were used as inspiration only; app opens directly to the workspace dashboard. | 2026-07-03
FE-002 | P0 | Foundation | Application Scaffold | Scaffold Next.js application in application/ | Frontend UI/UX Developer | Implementation approval; FE-001 | Next.js app exists under application/ with package scripts, app shell, routing baseline, lint/typecheck/test placeholders, and no Notion secrets | Implemented |  | Next.js app scaffolded under application/ with scripts for dev, lint, typecheck, test, e2e placeholder, and build. npm run lint, typecheck, test, and elevated build passed. | wiki/project-structure/project-structure.md; wiki/tdd/tdd.md | Build required elevated permission after sandbox EPERM during Next worker spawn. | 2026-07-03
FE-003 | P0 | Foundation | API Boundary | Create backend-only API client boundary for the frontend | Frontend UI/UX Developer | API contract drafted; FE-002 | Frontend calls only backend /api/v1 endpoints; no Notion SDK, database IDs as secrets, or server-only env reads appear in client code | Implemented |  | Added typed frontend API boundary in application/src/lib/api-client.ts targeting /api/v1. Static scan found no Notion SDK imports, token env reads, database ID variables, or direct Notion API URLs in frontend source. | wiki/api/api-specification.md; wiki/project-structure/project-structure.md | Frontend still uses mock DTO data until backend endpoints are available. | 2026-07-03
FE-004 | P0 | Planning | Auth UX | Define owner-only session and locked-state UX | Product & Planning Manager, Security Engineer, Frontend UI/UX Developer | MVP auth decision | Email sign-in and Google sign-in UX are documented, including signed-in, signed-out, loading, and unauthorized states | In Progress |  | Settings page now includes email and Google sign-in UX foundations plus session-state surface; full auth docs/security validation still pending. | wiki/product-specification/product-specification.md; wiki/api/api-specification.md | Requires backend/auth contract before completion. | 2026-07-03
FE-005 | P1 | MVP Read | Dashboard | Build finance dashboard and summary view | Frontend UI/UX Developer | Dashboard API; FE-003 | Dashboard shows latest sync status, account summaries, income/expense snapshots, and read-only computed values from backend responses | In Progress |  | Dashboard now uses a prototype-style Recent Transactions list while retaining the income/expense chart, spending donut, and budget usage components; lint, typecheck, tests, elevated build, and dashboard screenshots passed. |  | Still mock DTO data until the dashboard API is wired. | 2026-07-03
FE-006 | P0 | MVP Read | Accounts | Build accounts list, detail, and create/edit forms | Frontend UI/UX Developer | Accounts API; field mapping | Accounts show active records by default, support gallery/card and table views, and account forms adapt fields based on Account Type | In Progress |  | Accounts refined: badges show account type, non-credit table uses Total Income and Total Expense, and existing modals align read-only Total Income/Total Expense with Current Balance plus Credit Limit/Available Limit for credit/BNPL. Verified lint, typecheck, tests, build, and Accounts screenshot. |  | Backend API wiring, persisted mutations, and e2e modal/table coverage remain pending. | 2026-07-03
FE-007 | P1 | MVP Read | Income Categories | Build income category list and form workflow | Frontend UI/UX Developer | Income category API; field mapping | Source of Income can be created/edited; computed income metrics are read-only | In Progress |  | Income categories moved to Monthly Monitoring with table, donut chart, and card modes; Income Overview columns mirror Notion Source of Income, Monthly Earnings, and Earning Percentage; category items open edit modal. |  | Backend income category mutations still need the API contract. | 2026-07-03
FE-008 | P0 | MVP Write | Incomes | Build income create/edit/delete UI | Frontend UI/UX Developer | Income API; relation dropdowns; delete policy | Income UI supports Daily, Weekly, Monthly, and Annually views, frontend Account/Categories filters, normal income fields only, and excludes auxiliary income categories | In Progress |  | Income records are now clickable table rows; New Income opens a closable modal; dropdowns start with disabled account/category placeholders; computed values remain read-only. |  | Direct-save remains UI-only until the Income API is available. | 2026-07-03
FE-009 | P1 | MVP Write | Transactions | Build Transfer, Credit Card Payment, Alkansya, and Receivables workflow screens over Incomes data | Frontend UI/UX Developer | Transaction API/view filters; FE-008 | Transfer and Credit Card Payment have Monthly views with fixed non-editable categories; Alkansya and Receivables have Monthly views; required transacted account context is captured | In Progress |  | Transfer, Credit Card Payment, Alkansya, and Receivables now use list-first records and modal forms for new/edit/delete. Receivables hide outstanding rows after a receiving account is selected. |  | Workflow endpoints and e2e coverage still pending. | 2026-07-03
FE-010 | P1 | MVP Read | Expense Categories | Build expense category list and form workflow | Frontend UI/UX Developer | Expense category API; field mapping | Categories, Monthly Budget, Upcoming Budget, and Auxiliary are editable; spending and remaining metrics are read-only | In Progress |  | Expense categories moved to Monthly Monitoring with Simplified, MB Breakdown, chart, and card views; MB Simplified and Monthly Budget (v1) columns mirror Notion views, including totals where applicable. |  | Backend expense category mutations still need the API contract. | 2026-07-03
FE-011 | P0 | MVP Write | Expenses | Build expense create/edit/delete UI | Frontend UI/UX Developer | Expense API; relation dropdowns; delete policy | Expense UI supports Daily, Weekly, Monthly, Annually, Pasabuy, To pay, To buy, Installments, and CC Transactions views with frontend Account/Categories filters and conditional form fields | In Progress |  | Expense records are now clickable table rows; New Expense opens a closable modal; disabled placeholders added to account/category/status/frequency dropdowns; conditional credit/Pasabuy fields remain. |  | Direct-save remains UI-only until the Expense API is available. | 2026-07-03
FE-012 | P1 | MVP Write | Expense Scheduler | Build expense scheduler workflow screens over Expenses data | Frontend UI/UX Developer | Expense scheduler API/view filters; FE-011 | To-buy, to-pay, installment, scheduled expense, and related payment views reuse expense field rules and sync behavior | In Progress |  | Expense route includes To pay, To buy, Installments, and CC Transactions view-mode foundation. | wiki/product-specification/product-specification.md; wiki/database/data-model.md | Dedicated expense scheduler endpoint integration is still pending. | 2026-07-03
FE-013 | P0 | MVP Write | Sync UX | Build sync center and queued change indicators | Frontend UI/UX Developer | Sync status and commit APIs | UI shows last successful sync time, pending operation count, failed operation count, schema health, direct-save progress, and queued Sync button state | In Progress |  | Sync Center route shows last sync, pending count, failed count, schema health, queue commit action, and schema verification button foundation. | wiki/product-specification/product-specification.md; wiki/api/api-specification.md | Needs live sync/status APIs. | 2026-07-03
FE-014 | P0 | Hardening | Error UX | Build user-facing validation, schema drift, conflict, rate limit, and access errors | Frontend UI/UX Developer | Backend normalized error codes | Errors name the affected resource/property when available and give a clear next action without exposing stack traces or secrets | In Progress |  | Sync Center includes validation, schema drift, conflict, rate-limit, and access error examples without stack traces. | wiki/api/api-specification.md; wiki/tdd/tdd.md | Needs backend normalized error codes and e2e paths. | 2026-07-03
FE-015 | P0 | MVP Write | State Refresh | Implement refresh-from-fresh-snapshot behavior after writes | Frontend UI/UX Developer | Sync and resource mutation responses | After direct-save or queued sync, UI replaces local optimistic state with backend fresh Notion snapshot | In Progress |  | Sync action simulates replacing pending local state with a fresh backend snapshot timestamp. | wiki/tdd/tdd.md; wiki/product-specification/product-specification.md | Needs mutation responses that return fresh Notion-backed snapshots. | 2026-07-03
FE-016 | P1 | Hardening | Accessibility and Responsive QA | Harden layouts, forms, keyboard states, loading states, and empty states | Frontend UI/UX Developer, SQA Engineer | Core screens implemented | Primary workflows work on desktop and mobile, labels are readable, forms are keyboard usable, and validation is announced accessibly | In Progress |  | Added modal close controls, keyboard-clickable rows, disabled select placeholders, empty receivables state, and responsive chart/modal CSS; lint, typecheck, tests, elevated build, and screenshots passed. |  | Needs manual accessibility QA with live backend flows. | 2026-07-03
FE-017 | P0 | MVP Read | Monthly Monitoring | Build Monthly Monitoring read-only section | Frontend UI/UX Developer | FE-001; API monthly monitoring contract | Monthly Monitoring page shows month-level income, expense, gross margin, needs, wants, savings, budget category context, and income category context as read-only | In Progress |  | Monthly Monitoring now includes moved income and expense category management with table/chart/card views, Notion-matched MB Simplified and Monthly Budget (v1) columns, and totals rows. |  | Still awaits live monthly monitoring/category API data. | 2026-07-03

## backend-dev-plan
backend-dev-plan
Use Status, Blocked / Decision Needed, Verification / Evidence, and Acceptance Criteria together. A row is not done just because code exists. It is done when the acceptance criteria are verified.
ID | Priority | Phase | Epic | Work Item | Owner Role | Dependencies | Acceptance Criteria | Status | Blocked / Decision Needed | Verification / Evidence | Source Docs | Notes | Last Updated
BE-001 | P0 | Foundation | Service Scaffold | Scaffold NestJS service in service/ | Backend & Database Engineer | Implementation approval | NestJS service exists under service/ with health endpoint, scripts, lint/typecheck/test placeholders, and environment loading baseline | Not Started | Pending explicit backend implementation request | Build/lint/typecheck commands pass once tooling exists | wiki/project-structure/project-structure.md; wiki/tdd/tdd.md | Do this only after backend implementation approval. | 2026-07-04
BE-002 | P0 | Foundation | Configuration | Implement server-side configuration and secret loading | Backend & Database Engineer, Security Engineer | BE-001 | Notion token, database IDs, metadata store settings, and environment-specific options are read server-side only and validated on startup | Not Started |  | Unit tests and secret scan | wiki/tdd/tdd.md; wiki/api/api-specification.md; wiki/database/data-model.md | Do not expose token or server-only env values to application/ | 2026-07-03
BE-003 | P0 | Planning | Authentication | Decide and implement MVP auth/session model | Security Engineer, Backend & Database Engineer | MVP auth decision | Email sign-in and Google sign-in are implemented; write endpoints and sync commit are protected | Not Started |  | Auth tests for email sign-in, Google sign-in, session/me, logout, and protected routes | wiki/product-specification/product-specification.md; wiki/api/api-specification.md | Decision: auth is required for multi-user use | 2026-07-03
BE-004 | P0 | Foundation | Notion Adapter | Build Notion client wrapper and adapter boundary | Backend & Database Engineer | BE-002; Notion integration access | All Notion calls are centralized behind service adapters with normalized errors and rate-limit awareness | Not Started |  | Unit tests with mocked Notion client | wiki/tdd/tdd.md; wiki/api/api-specification.md |  | 2026-07-03
BE-005 | P0 | Foundation | Field Mapping | Implement Notion database/property mapping contract | Backend & Database Engineer | Live Notion schema verification | Mappings cover app sections, Notion data sources, exact property names, live select labels, auxiliary category exclusions, and fixed workflow category rules | Not Started | Needs live Notion schema confirmation before final mapping | Schema mapping tests and data-model update | wiki/database/data-model.md; wiki/tdd/tdd.md | Preserve exact Notion labels in mapping; UI may use friendly display labels | 2026-07-03
BE-006 | P0 | Foundation | Validation | Reject read-only, computed, hidden, and out-of-scope fields in mutations | Backend & Database Engineer, Security Engineer | BE-005 | Create/update/delete payloads accept writable fields only and return VALIDATION_ERROR for forbidden fields | Not Started |  | Unit and contract tests | wiki/api/api-specification.md; wiki/database/data-model.md |  | 2026-07-03
BE-007 | P0 | MVP Read | Accounts API | Build read-only account list/detail endpoints | Backend & Database Engineer | BE-004; BE-006 | Accounts support list/detail reads only; active-account default filtering works; current account state is returned as read-only; create/update/delete operations are absent or rejected | Not Started |  | Contract tests for list/detail reads and rejected account mutations | wiki/api/api-specification.md; wiki/database/data-model.md; wiki/product-specification/product-specification.md | Account setup, edits, inactive marking, and deletes happen in Notion only. | 2026-07-04
BE-008 | P1 | MVP Read | Income Categories API | Build read-only income category endpoints | Backend & Database Engineer | BE-004; BE-006 | Income Categories support list/detail reads for selectors, filters, category labels, and auxiliary category exclusion; create/update/delete operations are absent or rejected | Not Started |  | Contract tests for list/detail reads, auxiliary category filtering support, and rejected category mutations | wiki/api/api-specification.md; wiki/database/data-model.md; wiki/product-specification/product-specification.md | Category maintenance stays in Notion. Normal Income choices exclude auxiliary workflow categories. | 2026-07-04
BE-009 | P0 | MVP Write | Incomes API | Build income create/read/update/soft-delete endpoints | Backend & Database Engineer | BE-004; BE-006 | Income endpoints support normal income create/read/update/soft-delete and reject normal-income attempts to set transaction-only fields | Not Started |  | Integration tests for create/edit/delete | wiki/api/api-specification.md; wiki/database/data-model.md | Transacted Account and CC Payment Covered are reserved for specialized workflows | 2026-07-03
BE-010 | P1 | MVP Write | Transactions API | Build Transfer, Credit Card Payment, Alkansya, and Receivables APIs over Incomes data source/views | Backend & Database Engineer | BE-009; view filter contract | Workflow APIs apply fixed categories for Transfer and Credit Card Payment, include required transacted account context, and return Monthly workflow data | Not Started |  | Integration and contract tests | wiki/api/api-specification.md; wiki/database/data-model.md | Confirm Alkansya backing view during implementation discovery | 2026-07-03
BE-011 | P1 | MVP Read | Expense Categories API | Build read-only expense category endpoints | Backend & Database Engineer | BE-004; BE-006 | Expense Categories support list/detail reads for selectors, filters, auxiliary flags, monthly budget, upcoming budget, and category reporting config; create/update/delete operations are absent or rejected | Not Started |  | Contract tests for list/detail reads, budget/config fields, and rejected category mutations | wiki/api/api-specification.md; wiki/database/data-model.md; wiki/product-specification/product-specification.md | Category maintenance stays in Notion. App-calculated category reporting uses scoped Expense records plus budget config. | 2026-07-04
BE-012 | P0 | MVP Write | Expenses API | Build expense create/read/update/soft-delete endpoints | Backend & Database Engineer | BE-004; BE-006 | Expense endpoints support required view modes and validate conditional field groups for credit-card and Pasabuy flows | Not Started |  | Integration tests for create/edit/delete | wiki/api/api-specification.md; wiki/database/data-model.md | Credit-card fields require Credit Account or BYPL account context; Pasabuy fields require Pasabuy flow/category | 2026-07-03
BE-013 | P1 | MVP Write | Expense Scheduler API | Build scheduler workflows over Expenses data source/views | Backend & Database Engineer | BE-012; view filter contract | Scheduler endpoints reuse expense mapping and delete behavior while exposing to-buy, to-pay, installment, and scheduled workflows | Not Started |  | Integration and contract tests | wiki/api/api-specification.md; wiki/database/data-model.md | No separate canonical scheduler database | 2026-07-03
BE-014 | P0 | MVP Read | Sync Pull | Build pull-latest data normalization | Backend & Database Engineer | BE-004; BE-005 | Backend pulls latest app-scoped Notion data, normalizes it into app DTOs, and includes computed/read-only values in responses | Not Started |  | Integration tests with mocked Notion pages | wiki/tdd/tdd.md; wiki/api/api-specification.md |  | 2026-07-03
BE-015 | P0 | MVP Write | Sync Commit | Build queued sync commit orchestration | Backend & Database Engineer | BE-014; metadata store contract | Sync commit validates operations, writes to Notion, handles partial failure, pulls fresh snapshot, and returns applied/failed results | Not Started |  | Integration and contract tests | wiki/api/api-specification.md; wiki/tdd/tdd.md |  | 2026-07-03
BE-016 | P0 | Foundation | Metadata Store | Design and implement supporting metadata store | Backend & Database Engineer | Storage decision | PostgreSQL supports sync logs, pending mutations, conflicts, audit events, sessions if needed, and cached snapshots without becoming finance source of truth | Not Started |  | Data model docs and PostgreSQL persistence tests | wiki/database/data-model.md; wiki/tdd/tdd.md | Decision: PostgreSQL is primary durable metadata storage; Redis is optional for cache, rate limits, sessions, or queue coordination | 2026-07-03
BE-017 | P1 | Hardening | Conflict Detection | Detect stale edits and conflicts | Backend & Database Engineer | BE-014; metadata snapshots | Backend detects records changed in Notion after app load and returns CONFLICT_ERROR with user-safe details | Not Started |  | Integration tests with stale last-edited metadata | wiki/tdd/tdd.md; wiki/api/api-specification.md |  | 2026-07-03
BE-018 | P0 | Hardening | Schema Drift | Implement schema health and drift checks | Backend & Database Engineer | BE-005; BE-004 | System verifies data sources, properties, property types, relation targets, and select/status options; schema drift returns SCHEMA_DRIFT_DETECTED | Not Started |  | Schema status integration tests | wiki/api/api-specification.md; wiki/tdd/tdd.md |  | 2026-07-03
BE-019 | P1 | Hardening | Error Normalization | Normalize validation, Notion, access, rate-limit, conflict, and schema errors | Backend & Database Engineer, Security Engineer | BE-004; BE-006; BE-017; BE-018 | API returns stable error codes and user-safe messages without raw stack traces, tokens, or sensitive finance payloads | Not Started |  | Contract and security tests | wiki/api/api-specification.md; wiki/tdd/tdd.md |  | 2026-07-03
BE-020 | P1 | Hardening | Logging and Audit | Implement redacted operational logging and audit events | Backend & Database Engineer, Security Engineer | BE-016; BE-019 | Production logs redact sensitive finance payloads and credentials while preserving useful sync/error/audit metadata | Not Started |  | Security review and log redaction tests | wiki/database/data-model.md; wiki/tdd/tdd.md |  | 2026-07-03
BE-021 | P0 | MVP Read | Monthly Monitoring API | Build read-only Monthly Monitoring endpoints | Backend & Database Engineer | BE-004; BE-005 | GET monthly monitoring endpoints return read-only month-level monitoring data with related income and expense category context; mutation endpoints are absent or forbidden | Not Started |  | API integration and contract test results | wiki/api/api-specification.md; wiki/database/data-model.md | Do not expose edit paths for Monthly Monitoring normal app flows | 2026-07-03

## integration-dev-plan
integration-dev-plan
Use Status, Blocked / Decision Needed, Verification / Evidence, and Acceptance Criteria together. A row is not done just because code exists. It is done when the acceptance criteria are verified.
ID | Priority | Phase | Epic | Work Item | Owner Role | Dependencies | Acceptance Criteria | Status | Blocked / Decision Needed | Verification / Evidence | Source Docs | Notes | Last Updated
INT-001 | P0 | Foundation | Shared Contracts | Create shared DTOs, resource names, field access enums, and validation contracts | System Architect, Backend & Database Engineer, Frontend UI/UX Developer | Planning approval; API/data docs | shared/ exposes contracts used by application and service without importing frontend-only or backend-only modules | Not Started | Current phase says no application source code yet | Typecheck and dependency direction check | wiki/project-structure/project-structure.md; wiki/api/api-specification.md; wiki/database/data-model.md |  | 2026-07-03
INT-002 | P0 | Foundation | API Contract Alignment | Lock resource endpoint and response contracts before UI/backend parallel work | System Architect, Backend & Database Engineer, Frontend UI/UX Developer | INT-001 | Each app section has list/detail/mutation or read-only contract, including Monthly Monitoring and specialized monthly workflows | Not Started |  | Contract tests and API docs update | wiki/api/api-specification.md |  | 2026-07-03
INT-003 | P0 | Foundation | Frontend/Backend Local Wiring | Run application and service together locally | DevOps Engineer, Frontend UI/UX Developer, Backend & Database Engineer | FE-002; BE-001 | Local dev can start both runtimes with documented ports, env requirements, CORS/proxy behavior, and health checks | Not Started |  | Documented dev command and health check | wiki/commands/commands.md; wiki/project-structure/project-structure.md |  | 2026-07-03
INT-004 | P0 | MVP Write | Direct-Save Flow | Integrate form submit -> backend mutation -> Notion write -> pull latest -> UI refresh | Frontend UI/UX Developer, Backend & Database Engineer, SQA Engineer | FE-008 or FE-011; BE-009 or BE-012; BE-014 | Direct-save create/edit/delete operations refresh UI from fresh Notion data and show failure state on write or pull errors | Not Started |  | E2E direct-save test | wiki/product-specification/product-specification.md; wiki/tdd/tdd.md |  | 2026-07-03
INT-005 | P0 | MVP Write | Queued Sync Flow | Integrate pending operation queue and Sync button | Frontend UI/UX Developer, Backend & Database Engineer | FE-013; BE-015; metadata store | Queued operations can be reviewed, committed, partially failed, retried, and refreshed from fresh snapshot | Not Started |  | E2E queued sync test | wiki/product-specification/product-specification.md; wiki/api/api-specification.md |  | 2026-07-03
INT-006 | P0 | MVP Write | Fresh Snapshot Rule | Verify every mutation path re-pulls Notion before UI is current | System Architect, SQA Engineer | INT-004; INT-005 | No mutation path marks local UI current until backend returns fresh Notion-backed snapshot or explicit pull result | Not Started |  | E2E assertions around computed values | wiki/tdd/tdd.md; wiki/product-specification/product-specification.md |  | 2026-07-03
INT-007 | P0 | Planning | Non-Production Notion Workspace | Create and document a safe Notion test workspace/page | SQA Engineer, Backend & Database Engineer | User/owner Notion access | Destructive tests run only against the duplicated non-production Notion space shared with the test integration | Not Started | Duplicated Notion space will be provided; access details still need to be documented | Manual verification evidence | wiki/testing/test-specification.md; wiki/database/data-model.md | Decision: project owner will duplicate the current Notion setup for testing | 2026-07-03
INT-008 | P1 | MVP Read | Relation Dropdown Hydration | Connect account/category/relation selectors to backend data | Frontend UI/UX Developer, Backend & Database Engineer | BE resource list endpoints; FE forms | Account/category/relation selectors hydrate from backend data and respect active-account, auxiliary-category, fixed-category, and workflow-specific filtering rules | Not Started | Live Notion schema still needs verification after integration key is configured | Component and e2e form tests | wiki/product-specification/product-specification.md; wiki/database/data-model.md | Schema verification should be available through a button | 2026-07-03
INT-009 | P0 | Foundation | Exact Select Labels | Preserve live Notion select labels end to end | Backend & Database Engineer, Frontend UI/UX Developer, SQA Engineer | BE-005; schema verification | App labels and validation options preserve live Notion select labels exactly, including awkward labels | Not Started | Needs live Notion schema confirmation | Mapper tests and manual Notion verification | wiki/database/data-model.md; wiki/product-specification/product-specification.md | Do not silently prettify canonical select labels | 2026-07-03
INT-010 | P0 | MVP Write | Income/Transaction Delete Policy | Verify income-backed soft delete behavior end to end | Backend & Database Engineer, Frontend UI/UX Developer, SQA Engineer | BE-009; BE-010; FE-008; FE-009 | Delete updates title to include [Deleted: Amount], clears Gross Income, pulls latest data, and displays resulting state safely | Not Started |  | Integration, e2e, and manual Notion test | wiki/database/data-model.md; wiki/api/api-specification.md |  | 2026-07-03
INT-011 | P0 | MVP Write | Expense/Scheduler Delete Policy | Verify expense-backed soft delete behavior end to end | Backend & Database Engineer, Frontend UI/UX Developer, SQA Engineer | BE-012; BE-013; FE-011; FE-012 | Delete updates Purchase description to include [Deleted: Amount], clears Expense Amount, pulls latest data, and displays resulting state safely | Not Started |  | Integration, e2e, and manual Notion test | wiki/database/data-model.md; wiki/api/api-specification.md |  | 2026-07-03
INT-012 | P1 | MVP Write | Category Delete Policy | Verify category delete behavior end to end | Backend & Database Engineer, Frontend UI/UX Developer, SQA Engineer | BE-008; BE-011; FE-007; FE-010 | Income and expense categories can be deleted according to project policy with confirmation and fresh data pull | Not Started |  | Integration, e2e, and manual Notion test | wiki/api/api-specification.md; wiki/product-specification/product-specification.md |  | 2026-07-03
INT-013 | P0 | Planning | Account Delete Policy | Decide and implement account delete integration behavior | Product & Planning Manager, Security Engineer, Backend & Database Engineer, Frontend UI/UX Developer | Product decision | Account delete marks the account inactive by setting Inactive; no physical Notion delete is exposed | Not Started |  | Updated product/API/data docs and tests | wiki/product-specification/product-specification.md; wiki/api/api-specification.md; wiki/database/data-model.md | Decision: account delete means inactive | 2026-07-03
INT-014 | P1 | Hardening | Rate Limit and Retry Behavior | Handle Notion rate limits across UI and backend | Backend & Database Engineer, Frontend UI/UX Developer, SQA Engineer | BE-004; FE-014 | Rate-limited operations return NOTION_RATE_LIMITED, show retry guidance, preserve pending operations, and avoid duplicate writes | Not Started |  | Integration and e2e rate-limit tests | wiki/api/api-specification.md; wiki/tdd/tdd.md |  | 2026-07-03
INT-015 | P1 | Release | Runtime Configuration | Connect deployment/runtime env configuration across application and service | DevOps Engineer, Security Engineer | Scaffolds; BE-002; FE-003 | Vercel frontend, Render backend, PostgreSQL metadata storage, optional Redis, and local development/local production-style environment switching are documented | Not Started |  | Deployment dry-run or config validation once implementation exists | wiki/deployment/deployment.md; wiki/commands/commands.md | Decision: Vercel for frontend, Render for backend | 2026-07-03
INT-016 | P1 | MVP Read | Health and Schema Status UI | Surface backend health and schema status in UI | Frontend UI/UX Developer, Backend & Database Engineer | BE-018; FE-013 | UI can show healthy, degraded, and schema drift states using /health and /system/schema-status responses | Not Started |  | Contract and component tests | wiki/api/api-specification.md; wiki/product-specification/product-specification.md |  | 2026-07-03
INT-017 | P0 | Hardening | Conflict Handling Path | Integrate stale edit conflict UX and backend detection | Backend & Database Engineer, Frontend UI/UX Developer, SQA Engineer | BE-017; FE-014 | When Notion changed after app load, user sees conflict details and can refresh or retry without data loss | Not Started |  | Integration and e2e conflict tests | wiki/tdd/tdd.md; wiki/api/api-specification.md |  | 2026-07-03
INT-018 | P1 | Release | Release Readiness | Define and run cross-workstream release checklist | Product & Planning Manager, DevOps Engineer, SQA Engineer | Core MVP workflows implemented | Frontend, backend, integration, testing, docs, security, and deployment readiness are reviewed before production-like use | Not Started |  | Release checklist and evidence | wiki/testing/test-specification.md; wiki/deployment/deployment.md |  | 2026-07-03
INT-019 | P0 | MVP Read | Section Mapping | Verify app sections match Notion-backed views and filters | System Architect, Frontend UI/UX Developer, Backend & Database Engineer | FE section routes; BE resource APIs; Notion schema access | Dashboard, Accounts, Income, Expense, Monthly Monitoring, Transfer, Credit Card Payment, Alkansya, and Receivables routes map to the correct backend and Notion-backed data rules | Not Started |  | Route/API smoke evidence and updated docs | wiki/product-specification/product-specification.md; wiki/api/api-specification.md; wiki/database/data-model.md | Use read-only Notion verification before destructive writes | 2026-07-03

## testing-dev-plan
testing-dev-plan
Use Status, Blocked / Decision Needed, Verification / Evidence, and Acceptance Criteria together. A row is not done just because code exists. It is done when the acceptance criteria are verified.
ID | Priority | Phase | Epic | Work Item | Owner Role | Dependencies | Acceptance Criteria | Status | Blocked / Decision Needed | Verification / Evidence | Source Docs | Notes | Last Updated
TEST-001 | P0 | Planning | Test Tooling | Select test frameworks and command names | SQA Engineer, System Architect | Stack selected; scaffolding plan | Recommended lint, typecheck, unit, integration, contract, e2e, build, and schema verification commands are documented; exact commands are confirmed after scaffolding | Not Started |  | Updated commands and testing docs | wiki/testing/test-specification.md; wiki/commands/commands.md | Recommended: ESLint, TypeScript, Vitest, React Testing Library, Jest or Vitest for NestJS, Supertest, Playwright | 2026-07-03
TEST-002 | P0 | Foundation | Mapper and Field Access Unit Tests | Cover field classification and Notion property mappers | SQA Engineer, Backend & Database Engineer | BE-005; BE-006 | Tests prove writable fields are accepted and computed/read-only/hidden/out-of-scope fields are rejected | Not Started |  | Unit test report | wiki/testing/test-specification.md; wiki/database/data-model.md |  | 2026-07-03
TEST-003 | P1 | Foundation | Money and Date Unit Tests | Cover money/date parsing, formatting, and validation | SQA Engineer, Backend & Database Engineer, Frontend UI/UX Developer | Shared formatting contracts | Money values avoid unsafe float assumptions, dates use ISO strings, and invalid day/month/status cases are rejected | Not Started |  | Unit test report | wiki/api/api-specification.md; wiki/testing/test-specification.md |  | 2026-07-03
TEST-004 | P0 | MVP Write | Backend Integration Tests | Test backend resource endpoints with mocked Notion responses | SQA Engineer, Backend & Database Engineer | BE resource endpoints | List/detail/create/update/delete endpoints handle success, validation failure, Notion failure, and inaccessible record cases | Not Started |  | Integration test report | wiki/testing/test-specification.md; wiki/api/api-specification.md |  | 2026-07-03
TEST-005 | P0 | Foundation | Contract Tests | Test request/response and error contracts | SQA Engineer, Backend & Database Engineer, Frontend UI/UX Developer | INT-002 | Common response shape, resource DTOs, sync operation payloads, dashboard summary, and error codes remain stable | Not Started |  | Contract test report | wiki/api/api-specification.md; wiki/testing/test-specification.md |  | 2026-07-03
TEST-006 | P1 | MVP Read | Frontend Component Tests | Test form, table, sync status, and error components | SQA Engineer, Frontend UI/UX Developer | FE core components | Component tests cover forms, tables/cards, sync status, errors, view-mode toggles, active account default filtering, and conditional Income/Expense fields | Not Started |  | Frontend test report | wiki/testing/test-specification.md; wiki/product-specification/product-specification.md |  | 2026-07-03
TEST-007 | P0 | Foundation | E2E Harness | Set up e2e test runner and fixtures | SQA Engineer, DevOps Engineer | Application/service local wiring | E2E tests can run locally with mocked or non-production backend data and produce repeatable evidence | Not Started |  | E2E smoke test report | wiki/testing/test-specification.md; wiki/commands/commands.md |  | 2026-07-03
TEST-008 | P0 | MVP Write | Core E2E Workflows | Cover create/edit/delete/sync for incomes and expenses | SQA Engineer | FE/BE MVP write workflows | E2E tests cover create/edit/delete/sync for normal incomes and expenses plus Transfer, Credit Card Payment, and read-only Monthly Monitoring navigation | Not Started |  | E2E report | wiki/testing/test-specification.md; wiki/product-specification/product-specification.md |  | 2026-07-03
TEST-009 | P0 | Hardening | Schema Drift and Conflict Tests | Cover schema drift and stale edit paths | SQA Engineer, Backend & Database Engineer | BE-017; BE-018; FE-014 | Tests prove missing property, type change, inaccessible relation, missing select option, and stale edit paths return usable errors | Not Started |  | Integration and e2e reports | wiki/testing/test-specification.md; wiki/tdd/tdd.md |  | 2026-07-03
TEST-010 | P0 | Hardening | Security Tests | Verify secrets and sensitive data stay protected | Security Engineer, SQA Engineer | FE-003; BE-002; BE-019; BE-020 | Tests/scans confirm no Notion token in frontend code, browser storage, logs, stack traces, or public config | Not Started |  | Security review evidence | wiki/tdd/tdd.md; wiki/api/api-specification.md |  | 2026-07-03
TEST-011 | P1 | Planning | Manual Test Case Suite | Create manual QA cases under tests/ | SQA Engineer | Requirements stable enough for QA | Manual cases cover app-scoped data source mappings, relation dropdowns, computed fields hidden from forms, writes, delete policies, post-sync computed values, and auth/access errors | Not Started |  | Manual test case document | wiki/testing/test-specification.md; wiki/product-specification/product-specification.md |  | 2026-07-03
TEST-012 | P0 | MVP Write | Manual Notion Verification | Run manual tests against non-production Notion workspace/page | SQA Engineer, Backend & Database Engineer | INT-007; MVP write workflows | Destructive checks verify expected Notion page changes and app refresh behavior in the duplicated Notion space | Not Started | Duplicated Notion space will be provided; access details still need to be documented | Manual evidence with redacted screenshots/notes | wiki/testing/test-specification.md; wiki/database/data-model.md | Decision: use duplicated Notion setup for destructive manual tests | 2026-07-03
TEST-013 | P1 | Release | CI Pipeline | Add CI checks for lint, typecheck, tests, build, and docs | DevOps Engineer, SQA Engineer | Commands selected; project scaffolded | Pull requests run the agreed verification commands and fail on broken contracts or test failures after scaffolding | Not Started |  | CI run evidence | wiki/commands/commands.md; wiki/testing/test-specification.md | Exact CI commands are confirmed after scaffolding; recommended command names are documented | 2026-07-03
TEST-014 | P2 | Hardening | Coverage and Reporting | Define useful coverage thresholds and reporting | SQA Engineer | Test suites in place | Coverage focuses on mappers, validators, sync orchestration, and critical UI workflows without gaming line coverage | Not Started |  | Coverage report | wiki/testing/test-specification.md |  | 2026-07-03
TEST-015 | P1 | Release | Release Smoke Checklist | Create release smoke test checklist | SQA Engineer, Product & Planning Manager | MVP workflows implemented | Checklist covers login/owner state if any, pull latest, create/edit/delete, sync status, schema health, conflict path, and no production-secret exposure | Not Started |  | Smoke checklist and run evidence | wiki/testing/test-specification.md; wiki/deployment/deployment.md |  | 2026-07-03
TEST-016 | P2 | Hardening | Regression Matrix | Maintain regression matrix by resource/workflow | SQA Engineer | Core test cases identified | Regression matrix covers each section, view mode, conditional field rule, delete policy, sync path, and Notion schema dependency | Not Started |  | Regression matrix | wiki/testing/test-specification.md; wiki/product-specification/product-specification.md |  | 2026-07-03
TEST-017 | P0 | MVP Read | Section and Form Rules | Verify section view modes and conditional form behavior | SQA Engineer, Frontend UI/UX Developer | FE-006; FE-008; FE-009; FE-011; FE-017 | Manual and automated tests prove view modes, frontend filters, active account default, auxiliary income exclusion, fixed workflow categories, and conditional credit-card/Pasabuy fields | Not Started |  | Manual QA evidence plus component/e2e test report | wiki/testing/test-specification.md; wiki/product-specification/product-specification.md | This is the main guard against reintroducing raw Notion table complexity into the app UI | 2026-07-03