## Overview
Notable Finance — Performance Optimization Plan
Owner: System Architect • Author date: 2026-07-12 • Source: wiki/development-plan/architectural-critique-review.md
The complaint | After any CRUD on an income/expense item, the UI blocks and shows "Querying Notion…" for 3–7s. You cannot view or create other items until the sync finishes, even though only one row changed.
Root cause (3 layers) | 1) Backend nukes the ENTIRE 5-database cache after every mutation (refreshCache deletes all). 2) Frontend has no cache — refetch() hard-sets loading and the table disappears. 3) No optimistic updates — the UI waits on a full round-trip that re-fetches all 5 Notion DBs.
Design goal | Make CRUD feel instant and non-blocking. A single edit must not trigger a full 5-DB re-fetch, and the UI must never blank out for data it already has (stale-while-revalidate + optimistic updates).
Sequencing strategy (strangler, not big-bang)
• Phase 0 delivers the actual UX fix with ZERO new dependencies — ship it first for immediate relief.
• Phase 1–2 remove redundant reference-data fetches and harden the backend cache.
• Phase 3 adopts @tanstack/react-query as the durable caching layer (ADR gate before starting).
• Phase 4 is the maintainability refactor (split the 5,856-line workspace + 965-line NotionService).
• Phase 5 is polish (skeletons, debounce, error boundaries, pagination, dynamic months).
• Each phase is independently shippable. Do NOT start a later phase before its dependencies are Done.
Phases at a glance
Phase | Outcome • primary assignee
P0 — Instant relief ✅ 6/7 | DONE (code): targeted invalidation + single-collection refill + silent refetch + optimistic create/update/delete. P0-7 live QA BLOCKED on configured Notion/Neon env. See p0-implementation-note.md. • Backend + Frontend
P1 — Ref-data hoist ✅ 4/4 | DONE & VERIFIED live: FinanceDataProvider in the ROOT layout fetches accounts + categories once per session; client-side navigation no longer re-fetches reference data. See p1-implementation-note.md. • Frontend
P2 — Cache hardening | Per-collection TTL; single-resource refresh instead of all-or-nothing. • Backend
P3 — React Query | Durable caching, dedup, optimistic mutations, background refetch. • Frontend (ADR by Architect)
P4 — Refactor | Split workspace monolith + NotionService god class behind stable contracts. • Frontend + Backend
P5 — Polish | Skeletons, debounce, error boundaries, pagination, dynamic months. • Frontend
How to use this workbook
• Task Board sheet = the single source of truth. Update the Status column (dropdown) as work moves.
• Assignee column names the agent that should execute the task (see Assignees sheet for handoffs).
• Context / Implementation notes column gives each agent the exact files, lines, and definition of done.
• Respect Depends On — a task is not startable until its dependencies are Done.
• Status colours are automatic: Done=green, In Progress=amber, Blocked=red, In Review=blue.

## Task Board
Task Board — update the Status column as work progresses
ID | Phase | Task | Assignee | Depends On | Priority | Effort | Layer | Context / Implementation notes (files • what to do) | Acceptance criteria (definition of done) | Status
P0-1 | P0 — Instant relief | Replace nuclear cache invalidation with targeted invalidation | backend-database-engineer | — | P0 Critical | M | Backend | File: service/src/notion/notion.service.ts. Today refreshCache() (line ~161) does liveCaches.delete(key) — wiping ALL 5 collections. Add refreshCacheFor(userId, resource) that mutates the existing LiveCache in place: if resource isIncomeBacked → clear only cache.incomes; if isExpenseBacked → clear only cache.expenses; leave accounts/incomeCategories/expenseCategories intact. Wire create() (~241), update() (~263), delete() (~302) to call refreshCacheFor(userId, resource) instead of refreshCache(userId). Keep full refreshCache only for pull() (~322) and explicit sync. Use an empty array as the 'stale' sentinel OR add a per-collection dirty flag — coordinate with P2-1 which formalises TTL. | A single income/expense mutation no longer clears accounts/categories from cache. Next list() call re-fetches only the mutated collection. Existing unit/e2e tests pass. | Done
P0-2 | P0 — Instant relief | Add single-collection refresh path to loadLive() | backend-database-engineer | P0-1 | P0 Critical | M | Backend | File: service/src/notion/notion.service.ts, loadLive() (~96-130) currently always Promise.all's all 5 queryDatabase calls when the cache key is absent. Add the ability to refill just one collection when only it was invalidated: e.g. loadLiveCollection(userId, 'incomes') that runs client.queryDatabase('incomes') and writes cache.incomes only. When refreshCacheFor cleared only cache.incomes, the next read must fetch ONLY incomes — not all 5 DBs. Preserve the existing fallback-to-null-on-error behaviour. | After editing one income, the backend issues exactly ONE Notion queryDatabase call (incomes) on the following read, verified via logs. Accounts/categories are served from memory. | Done
P0-3 | P0 — Instant relief | Add silent (stale-while-revalidate) refetch mode to useApiData | frontend-ui-ux-developer | — | P0 Critical | M | Frontend | File: application/src/lib/use-data.ts. refetch() (~100-120) immediately does setState({status:'loading'}), which blanks the table and shows the spinner. Change refetch to accept an option: refetch({ silent }: { silent?: boolean } = {}). When silent, do NOT set loading — keep the current success data on screen and only swap in new data when the promise resolves (stale-while-revalidate). Keep the non-silent path for first load / explicit sync. Update the return type so callers can pass the flag. | Calling refetch({silent:true}) never renders <LoadingBlock>. The previously loaded rows stay visible during the background fetch, then update in place. | Done
P0-4 | P0 — Instant relief | Add applyLocal() optimistic-merge helper to useApiData | frontend-ui-ux-developer | P0-3 | P0 Critical | M | Frontend | File: application/src/lib/use-data.ts. Expose an applyLocal(updater: (prev: T) => T) from the hook that synchronously updates state.data without a network call (guarded to only run when status==='success'). This lets a page merge the record returned by the API straight into the visible list. Return { state, refetch, applyLocal } from useApiData and thread it through useIncomes/useExpenses/useWorkflowRecords. | applyLocal((rows)=>...) updates the on-screen list instantly with no loading flash and no network call. Type-safe; no regressions in existing consumers. | Done
P0-5 | P0 — Instant relief | Optimistic create/update on save (income, expense, workflow) | frontend-ui-ux-developer | P0-4 | P0 Critical | M | Frontend | File: application/src/components/finance-workspace.tsx. handleSaveIncome (~1949, refetch at ~1974), handleSaveExpense (~2378, ~2413), handleSaveWorkflow (~3115, ~3149) currently do: setModal(null); await refetch(). The API already returns the full mapped record (pageToIncomeRecord/pageToExpenseRecord). New flow: on success → setModal(null) → applyLocal() to insert-or-replace the returned record in the visible list → refetch({silent:true}) in the background to pick up computed fields. Remove the blocking await refetch(). | Saving an income/expense/workflow item closes the modal and shows the new/updated row immediately (<150ms perceived). No spinner. Background refetch reconciles computed fields silently. | Done
P0-6 | P0 — Instant relief | Optimistic soft-delete | frontend-ui-ux-developer | P0-4 | P0 High | S | Frontend | File: application/src/components/finance-workspace.tsx delete handlers (paired with the save handlers above). Backend delete() is a soft-delete that returns the record with {deleted:true}. On delete success → applyLocal() to remove the row (or mark it deleted per current view rules) from the visible list immediately → refetch({silent:true}). Do not block on the round-trip. | Deleting a row removes it from the table instantly with no spinner; background refetch confirms. Deleted item stays gone after reconcile. | Done
P0-7 | P0 — Instant relief | Verify Phase 0: non-blocking, no-spinner CRUD | sqa-engineer | P0-1,P0-2,P0-3,P0-5,P0-6 | P0 High | S | QA | Run the app (see .claude/launch.json / preview). Exercise create, edit, delete on Income and Expense while watching backend logs and the network tab. Confirm: (a) no 'Querying Notion…' spinner after a save/delete; (b) the mutated row appears/updates/disappears instantly; (c) backend makes ONE queryDatabase call (mutated collection) on the follow-up read, not five; (d) you can immediately start another CRUD without waiting. | Documented before/after: perceived save latency drops from 3–7s to <0.5s; Notion API calls per edit drop from ~2 full 5-DB round-trips to 1 write + 1 single-collection read. No functional regressions. | Blocked
P1-1 | P1 — Ref-data hoist | Design FinanceDataProvider context contract | system-architect | — | P1 Medium | S | Architecture | Reference data (accounts, income categories normal+all, expense categories) changes rarely but useLiveCollections() (finance-workspace.tsx ~299) re-fetches it on every page mount (Dashboard, Income, Expense, Workflow, Monitoring). Define the shape of a FinanceDataProvider: what it exposes (activeAccounts, allAccounts, normalIncomeCategories, allIncomeCategories, expenseCategories, plus a refreshReferenceData()), where it mounts (wrapping the workspace, inside AuthProvider), and its invalidation triggers (only when a category/account is mutated). | One-page contract in wiki/development-plan agreed by FE: provider surface, mount point, and when reference data is refreshed. Handoff note to P1-2. | Done
P1-2 | P1 — Ref-data hoist | Implement FinanceDataProvider + useFinanceData() | frontend-ui-ux-developer | P1-1 | P1 Medium | M | Frontend | Create application/src/lib/finance-data-context.tsx (or similar). Fetch accounts + categories ONCE on mount using the existing api-client, store in context, expose useFinanceData(). Mount the provider around the workspace sections. Include a refreshReferenceData() the account/category CRUD paths can call after a mutation. | Provider fetches reference data once per session. useFinanceData() returns cached values with no network call. Reference CRUD triggers a targeted refresh. | Done
P1-3 | P1 — Ref-data hoist | Migrate useLiveCollections consumers to context | frontend-ui-ux-developer | P1-2 | P1 Medium | M | Frontend | Replace the internals of useLiveCollections() (finance-workspace.tsx ~299) — and its call sites (~1055, ~1870, ~2195, ~2976, ~3313) — to read from useFinanceData() instead of firing useAccounts/useIncomeCategories/useExpenseCategories per mount. Keep the same returned field names to minimise churn at call sites. | Navigating between Dashboard/Income/Expense/Workflow/Monitoring issues zero reference-data API calls after the first load (verified in network tab). | Done
P1-4 | P1 — Ref-data hoist | Verify reference data fetched once | sqa-engineer | P1-3 | P1 Low | S | QA | Navigate across all five sections and confirm accounts/categories are fetched exactly once per session, and that adding/editing an account or category still refreshes the dropdowns. | Network trace shows a single reference-data fetch per session; category/account edits still reflected in forms. | Done
P2-1 | P2 — Cache hardening | Add per-collection TTL / freshness to LiveCache | backend-database-engineer | P0-1 | P2 Medium | M | Backend | File: service/src/notion/notion.service.ts, LiveCache interface (~64-70) is a flat struct with no timestamps. Introduce per-collection freshness (e.g. { data, fetchedAt } per collection, or a parallel Map of fetchedAt). A collection is served from memory while fresh (TTL 30–60s, configurable via AppConfigService); stale collections refetch themselves on next read. This replaces the empty-array sentinel from P0-1 with an explicit freshness model. | Each collection has an independent freshness clock. Reads within TTL hit memory; stale reads refetch only that collection. TTL is configurable. | Not Started
P2-2 | P2 — Cache hardening | Refactor loadLive() into per-resource loaders | backend-database-engineer | P2-1 | P2 Medium | M | Backend | Break the all-or-nothing Promise.all in loadLive() (~107-114) into discrete loaders keyed by resource so the cache manager can refill any single collection. Keep a loadAll() convenience for cold start and pull(). Consider extracting a small CacheManager helper — this de-risks the P4 NotionService split. | loadLive orchestrates per-resource loaders; no code path fetches all 5 DBs except cold start and explicit sync. Behaviour verified by logs. | Not Started
P2-3 | P2 — Cache hardening | Verify single-resource refresh + TTL | sqa-engineer | P2-2 | P2 Low | S | QA | Confirm: stale-collection reads refetch only that collection; within-TTL reads hit memory (no Notion call); cold start still loads everything. | Log-verified: correct number of Notion queries for cold start, within-TTL read, and post-mutation stale read. | Not Started
P3-1 | P3 — React Query | ADR + go/no-go: adopt @tanstack/react-query v5 | system-architect | P0-7 | P3 High | S | Architecture | Write an ADR (wiki) deciding whether to adopt @tanstack/react-query v5 as the durable frontend cache. Cover: query-key scheme (['incomes', params], ['expenses', params], ['accounts'], etc.), the invalidation map (which mutation invalidates which queries, incl. cross-section: editing an expense must invalidate dashboard + monthly-monitoring), staleTime/gcTime defaults, and the strangler migration order. Decision gate: proceed only if Phase 0 relief is deemed insufficient OR the team wants the durable layer. Record the rejected alternative (keep hand-rolled useApiData). | Signed ADR with query keys, invalidation map (including cross-section staleness), defaults, and migration order. Explicit go/no-go recorded. | Not Started
P3-2 | P3 — React Query | Install React Query + QueryClientProvider | frontend-ui-ux-developer | P3-1 | P3 High | S | Frontend | Add @tanstack/react-query to application/package.json. Create a QueryClientProvider at the app root (inside AuthProvider) with defaults from the ADR (staleTime ~30s, gcTime, retry policy). Keep the existing api-client as the fetch layer. | QueryClient mounts app-wide; defaults match the ADR; app builds and runs with no behavioural change yet. | Not Started
P3-3 | P3 — React Query | Migrate reads to useQuery | frontend-ui-ux-developer | P3-2 | P3 High | L | Frontend | Port the read hooks (useIncomes, useExpenses, useWorkflowRecords, useDashboardData, useMonthlyMonitoring) to useQuery with the ADR's query keys, wrapping the existing api-client calls. Preserve the params→key behaviour that currently lives in useApiData's `key` argument. Reference data (Phase 1) can move to useQuery too or stay in context — per ADR. | All list/detail reads go through React Query with stale-while-revalidate. No blank tables on refetch. Existing views render identically. | Not Started
P3-4 | P3 — React Query | Migrate mutations to useMutation (optimistic + rollback + invalidation) | frontend-ui-ux-developer | P3-3 | P3 High | L | Frontend | Convert save/delete handlers to useMutation with onMutate (optimistic cache update via setQueryData + snapshot), onError (rollback), onSettled (invalidateQueries per the ADR invalidation map, including dashboard + monthly-monitoring for cross-section freshness). This supersedes the hand-rolled optimistic logic from P0-5/P0-6. | CRUD is optimistic with automatic rollback on failure. Editing an expense updates Dashboard and Monthly Monitoring without a manual refresh (cross-section staleness fixed). | Not Started
P3-5 | P3 — React Query | Remove legacy useApiData | frontend-ui-ux-developer | P3-4 | P3 Medium | M | Frontend | Once all reads/mutations are migrated, delete useApiData and the applyLocal/silent-refetch shims (P0-3/P0-4) that React Query now supersedes. Update imports. | No references to useApiData remain. Bundle has one caching mechanism. Lint/build clean. | Not Started
P3-6 | P3 — React Query | Full CRUD + cross-section regression | sqa-engineer | P3-4 | P3 High | M | QA | Regress every CRUD path on Income, Expense, and all Workflow sections. Verify optimistic UI, rollback on forced failure, request dedup (two components → one fetch), and that Dashboard/Monthly Monitoring reflect edits without navigation. | All CRUD passes; forced-failure rolls back cleanly; no duplicate in-flight requests; cross-section numbers stay consistent. | Not Started
P4-1 | P4 — Refactor | Boundary plan: split workspace monolith + NotionService god class | system-architect | P3-6 | P4 Medium | M | Architecture | finance-workspace.tsx is 5,856 lines; NotionService is 965 lines with list/create/update/delete/sync/schema/dashboard/monitoring responsibilities. Produce a module-boundary plan: FE → components/pages/*.tsx (dashboard, income, expense, workflow, monthly-monitoring, accounts, sync, settings) + components/ui/* (DataTable, FormModal, Panel, MetricCard). BE → NotionReadService, NotionMutationService, CacheManager (from P2), ReportingService (dashboard/monitoring), keeping controller contracts stable. Define the migration order and public interfaces; keep each PR reviewable. | Ownership table + interface sketch for both splits, with a reviewable incremental sequence and no controller-contract breakage. | Not Started
P4-2 | P4 — Refactor | Extract page + shared UI components from workspace | frontend-ui-ux-developer | P4-1 | P4 Medium | L | Frontend | Following P4-1, move each page component into components/pages/ and shared UI into components/ui/. Migrate incrementally (one page per PR), keeping behaviour identical. Do not mix this with feature changes. | finance-workspace.tsx becomes a thin router/shell; each page and shared widget lives in its own file. UI unchanged; build/lint clean. | Not Started
P4-3 | P4 — Refactor | Split NotionService behind stable contracts | backend-database-engineer | P4-1 | P4 Medium | L | Backend | Following P4-1, extract read, mutation, cache, and reporting responsibilities from NotionService into focused services. Controllers keep delegating through the same method signatures (add a thin facade if needed). Land incrementally. | NotionService responsibilities are split into cohesive services; controller contracts unchanged; all backend tests pass. | Not Started
P4-4 | P4 — Refactor | Post-refactor regression | sqa-engineer | P4-2,P4-3 | P4 Medium | M | QA | Full functional regression after the structural split — every page renders, every CRUD path works, reporting matches pre-refactor numbers. | No behavioural diff vs. pre-refactor baseline; all suites green. | Not Started
P5-1 | P5 — Polish | Debounce filter changes | frontend-ui-ux-developer | P3-3 | P5 Low | S | Frontend | Filter/account/category toggles currently fire a request per change. Debounce (~250–300ms) so rapid toggling issues one request. With React Query, dedup already helps; add debounce on the input side. | Rapidly toggling filters issues a single settled request, not one per keystroke/click. | Not Started
P5-2 | P5 — Polish | Replace text spinner with loading skeletons | frontend-ui-ux-developer | P3-3 | P5 Low | M | Frontend | Replace the 'Querying Notion…' text spinner with skeleton rows matching the table/card layout to prevent layout shift on the rare true-loading (cold) path. | Cold-load shows skeletons matching final layout; no layout shift; spinner text removed. | Not Started
P5-3 | P5 — Polish | Add error boundaries | frontend-ui-ux-developer | P4-2 | P5 Low | S | Frontend | Wrap page sections in React error boundaries so a component crash shows a recoverable error panel instead of taking down the whole workspace. | A thrown error in one page renders a scoped fallback; the rest of the app stays usable. | Not Started
P5-4 | P5 — Polish | Pagination / virtualization for large lists | frontend-ui-ux-developer | P3-3 | P5 Low | M | Frontend | Income/expense lists render every row at once. Add pagination or virtual scrolling so hundreds of records don't degrade render performance. Coordinate page size with backend list params. | Large datasets (500+ rows) scroll smoothly; initial render stays fast. | Not Started
P5-5 | P5 — Polish | Dynamic month list | frontend-ui-ux-developer | — | P5 Low | S | Frontend | File: application/src/lib/finance-data.ts has a hardcoded months array (2026-01..2026-07). Generate it dynamically from the current date (and/or earliest record) so the selector isn't frozen in time. | Month selector reflects the current date automatically without code edits. | Not Started

## Assignees & Legend
Assignees (agents)
Agent | Responsibility on this plan
system-architect | Owns design decisions, ADRs, and module-boundary plans (P1-1, P3-1, P4-1). Hands implementation to FE/BE.
backend-database-engineer | Owns service/ (NestJS + NotionService). Cache invalidation, loadLive granularity, TTL, backend split.
frontend-ui-ux-developer | Owns application/ (Next 16 + React 19). Optimistic updates, context provider, React Query, UI polish, refactor.
sqa-engineer | Owns verification tasks — measures before/after, runs CRUD + cross-section regressions.
Status legend
Status | Meaning
Not Started | Not begun. Blocked-by dependencies may still be open.
In Progress | Actively being worked by the assignee.
Blocked | Cannot proceed — dependency open or decision pending.
In Review | Implementation done; under review/QA.
Done | Merged and verified. Unblocks dependents.
Priority / Effort legend
• Priority: P0 Critical → P5 Low, matching the phase. P0 is the actual UX fix — do first.
• Effort: S ≈ <0.5 day, M ≈ 0.5–1.5 days, L ≈ 2–4 days (single focused agent).
• Depends On lists task IDs that must be Done before starting.