## Overview
Notable Finance — Desktop App Progress
Offline-first Electron desktop client. Local SQLite is the source of truth; Notion is a bidirectional mirror. Phases 0-1 complete and verified on 2026-07-21: the app is a fully usable offline daily driver (local CRUD, real-time derived balances, 9 sections, multi-window). Next: Phase 2 (Notion onboarding + push).
Overall Progress
Total items | 22 | Done | 9 | % Complete | 40.91%
Progress by Phase
Phase | Total | Not Started | In Progress | Done | Blocked
Phase 0 — Scaffold & shared logic | 4 | 0 | 0 | 4 | 0
Phase 1 — Offline app (fully usable, no sync) | 5 | 0 | 0 | 5 | 0
Phase 2 — Onboarding + Push | 3 | 3 | 0 | 0 | 0
Phase 3 — Pull | 3 | 3 | 0 | 0 | 0
Phase 4 — Reconcile + Conflict | 4 | 4 | 0 | 0 | 0
Phase 5 — Package | 3 | 3 | 0 | 0 | 0
Total | 22 | 13 | 0 | 9 | 0
Milestones
Milestone | Scope | Items | Done | % Complete | Reaching it means
M1 — Offline app | Phase 0, Phase 1 | 9 | 9 | 100% | Usable offline; real-time balances.
M2 — Backup sync | Phase 2, Phase 3 | 6 | 0 | 0% | Push + pull working (one-directional feel).
M3 — Full sync | Phase 4 | 4 | 0 | 0% | Bidirectional reconcile + conflict resolver.
M4 — Shippable | Phase 5 | 3 | 0 | 0% | Packaged installers for mac/linux/windows.
Status Legend
Not Started | Planned but not yet begun.
In Progress | Actively being worked; acceptance not yet met.
Done | Complete and verified against its acceptance criterion.
Blocked | Cannot proceed without a dependency, decision, or access.

## Development Plan
Notable Finance — Desktop Development Plan
Work items from wiki/desktop/development-plan.md. Edit the Status (dropdown) and Notes columns to track progress. Updated 2026-07-21.
Phase | ID | Work Item | Acceptance Criteria | Status | Notes / Evidence
Phase 0 | 0.1 | pnpm workspace; notable-finance-app with electron-vite (main/preload/renderer) | App window boots with HMR | Done | Verified 2026-07-21: pnpm workspace + electron-vite scaffold; build & typecheck clean; Electron window boots with Vite HMR at localhost:5173.
Phase 0 | 0.2 | better-sqlite3 + drizzle wired; migrations run on start | Empty DB created in userData | Done | Verified 2026-07-21: better-sqlite3 (rebuilt for Electron ABI) + drizzle wired; migrations run on start; DB created at userData/notable-finance-app/notable-finance.sqlite with all 10 tables.
Phase 0 | 0.3 | Copy domain/types/mapping/reporting from web into src/main/domain + src/shared | Unit tests for derivations pass | Done | Verified 2026-07-21: DTO types + resource-utils + local derivations in src/shared + src/main/domain; 16 derivation unit tests pass (vitest). Notion property mapping deferred to Phase 2 (bundled with the Notion adapter).
Phase 0 | 0.4 | contextBridge preload + IPC skeleton | Renderer calls a no-op window.api channel | Done | Verified 2026-07-21: contextBridge preload + ipcMain.handle skeleton (app:ping, db:health) with the ApiResult envelope; renderer roundtrip returns pong + the live table list.
Phase 1 | 1.1 | SQLite schema for all resources + sync columns | Schema matches local-data-schema.md | Done | Verified 2026-07-21: schema completed with pasabuy columns (migration 0001); all tables + sync columns per local-data-schema.md.
Phase 1 | 1.2 | Local CRUD for incomes/expenses/scheduler (instant write, dirty) | Create/edit/soft-delete works offline | Done | Verified 2026-07-21: repositories with instant writes, sync_state=dirty, mutation_queue journal, soft-delete via title rewrite; validation in main; full IPC surface. Live-run harness exercised create/update/soft-delete.
Phase 1 | 1.3 | Derived values (balances, budgets, net, monthly) computed from SQLite | Numbers match golden tests; update on edit | Done | Verified 2026-07-21: live golden checks PASS (income 50,000 / expense 11,500 / margin 38,500 / cash flow 73,000; credit balance -8,000, available 42,000); recompute + derived:updated on every edit; 27 unit tests green.
Phase 1 | 1.4 | Ported renderer pages (Dashboard, Accounts, Income, Expense, Monitoring, Transfer, CC Payment, Alkansya, Receivables) | Sections render from local data | Done | Verified 2026-07-21: all 9 sections render from local SQLite over window.api with the web view semantics (fixed categories Transfer/CC Payment/Savings, receivables = no account, income excludes auxiliary). Re-expressed UI (not pixel-ported); full CRUD forms + scheduler panel.
Phase 1 | 1.5 | Multi-window; changes reflect across windows | Two windows stay consistent | Done | Verified 2026-07-21: New Window (menu Cmd/Ctrl+N + IPC); records:changed/derived:updated broadcast to all windows; live run showed 2 windows each receiving all 18 events and refetching.
Phase 2 | 2.1 | Notion Connect: token via safeStorage; discover + map databases | Token stored in keychain, never in renderer | Not Started
Phase 2 | 2.2 | Schema verification (drift report) | Verify passes on the mapped workspace | Not Started
Phase 2 | 2.3 | Push: create/update/soft-delete to Notion (writable fields only) | Dirty records reach Notion; ids stored; idempotent | Not Started
Phase 3 | 3.1 | Initial pull populates SQLite | Local store matches Notion after onboarding | Not Started
Phase 3 | 3.2 | Incremental pull via Search since last_pull_cursor | Only changed pages fetched; cursor persists | Not Started
Phase 3 | 3.3 | Reference cache (accounts/categories) refresh on pull | Selectors reflect Notion | Not Started
Phase 4 | 4.1 | Three-way merge (base/local/remote); auto-merge disjoint fields | Scenario matrix tests pass | Not Started
Phase 4 | 4.2 | Conflict detection + log + resolver UI (prompt) | Same-field conflict prompts and resolves | Not Started
Phase 4 | 4.3 | Sync modes (manual + interval push/pull); status indicator; badges | Status/badges per offline-and-state-model.md | Not Started
Phase 4 | 4.4 | Mutation queue durability + rate-limit backoff | Crash/429 simulations pass | Not Started
Phase 5 | 5.1 | electron-builder for mac/linux/windows; native rebuild | Installers produced; app runs unsigned | Not Started
Phase 5 | 5.2 | Playwright + Electron e2e for core flows | E2E suite green | Not Started
Phase 5 | 5.3 | CHANGELOG + versioning | v0.1.0 tagged | Not Started